## ProjectSchedule
Communities of Excellence
Location | Project Start: | 2020-07-20
Project Lead | Today: | 2020-11-12
| Display Week: | 0 |  |  | 2020-07-13 | [6 empty] | 2020-07-20 | [6 empty] | 2020-07-27 | [6 empty] | 2020-08-03 | [6 empty] | 2020-08-10
[5 empty] | 2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19 | 2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26 | 2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16
TASK | PROGRESS | START | WORK DAYS | END | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Communities of Excellence Project |  | 2020-07-20 | 52 | 2020-09-29
SETUP
Establishing a project
0101 Community Profile | 30% | 2020-07-20 | 13 | 2020-08-05 | 2020-08-05: 30%
0102 Project Brief | 100% | 2020-07-20 | 1 | 2020-07-20 | 2020-07-20: 300%
Assessing the landscape
0201 Digital Health Checklist | 80% | 2020-07-21 | 19 | 2020-08-15 | 2020-08-15: 80%
0202 Social Inclusion Needs Analysis | 20% | 2020-07-21 | 1 | 2020-07-21 | 2020-07-21: 300%
0203 Communications & Engagement Channel Audit | 40% | 2020-07-21 | 22 | 2020-08-19
Planning the Project
0301 Project Initiation Document | 10% | 2020-07-22 | 3 | 2020-07-25 | 2020-07-25: 10%
0302 Project Schedule | 15% | 2020-07-22 | 1 | 2020-07-22 | 2020-07-22: 300%
0303 Benefits Realisation Plan | 100% | 2020-07-22 | 12 | 2020-08-06 | 2020-08-06: 100%
0304 Monitring and Evaluation Plan | 15% | 2020-07-22 | 5 | 2020-07-27
Engaging the community
0401 Targeted Social Inclusion & Engagement Plan | 0% | 2020-07-20 | 5 | 2020-07-26 | bar: 2020-07-26
0402 Accessibility & Cultural Competency Plan | 0% | 2020-07-20 | 3 | 2020-07-22 | bar: 2020-07-22
0403 Co-design & Consumer Collaboration Plan | 0% | 2020-07-20 | 15 | 2020-08-08 | bar: 2020-08-08
0404 Patient Journey Mappings | 0% | 2020-07-20 | 3 | 2020-07-22 | bar: 2020-07-22
Forming a steering committee
0501 Steering Committee Setup Guide | 0% | 2020-07-23 | 7 | 2020-08-01 | bar: 2020-08-01
0502 Terms of Reference | 0% | 2020-07-23 | 6 | 2020-07-30 | bar: 2020-07-30
0503 Standing Agenda | 0% | 2020-07-23 | 1 | 2020-07-23 | 2020-07-23: 300%
0504 Meeting Minutes | 0% | 2020-07-23 | 10 | 2020-08-05 | bar: 2020-08-05
Promoting the project
0601 Trademark License Agreement | 0% | 2020-07-24 | 6 | 2020-07-31 | bar: 2020-07-31
0602 Localisable Promotional Materials | 0% | 2020-07-24 | 16 | 2020-08-16 | bar: 2020-08-16
0604 Media Notices | 0% | 2020-07-24 | 1 | 2020-07-24 | 2020-07-24: 300%
Monitoring and evaluating initiatives
0701 Consumer Survey | 0% | 2020-07-25 | 5 | 2020-08-01 | bar: 2020-08-01
0702 Provider Survey | 0% | 2020-07-25 | 1 | 2020-07-27 | 2020-07-27: 300%
0703 Progress Report | 0% | 2020-07-25 | 0 | 2020-07-26 | bar: 2020-07-26
ADOPTION
Insert new rows ABOVE this one

## README
Overview
1 | Location | Input the location of the Community of Excellence
2 | Project Lead | Input the project lead (typically the Digital Health Manager)
3 | Project Start | Input the date of project commencement.
4 | Today | This is automatically generated as today's date.
5 | Display Week | Change this number manually or with the slider to scroll the chart. The number represents the number of weeks into the project the chart starts from.
Task List
1 | Tasks | Tasks can be organised however is relevant, but here we recommend organising by Guidebook steps/deliverables to follow along. Only documents are included currently, but other tasks should be included here. Subtasks should be indented for easier reading.
2 | Groups | Each task can be grouped by its subtasks for easier navigation
3 | Progress | Progress is manually updated as a % completed, which will change the fill in the cell. Completed tasks are automatically marked with a tick.
4 | Start and End | These dates are input as the expected start and end of work on an item.
5 | Work Days | These are the total weekdays (M-F) between the Start and End. This is automatically calculated, but can be used to adjust the end date.
6 | Inserting new rows | As long as new rows are inserted above this line they will copy the formatting of the rows above.
Calendar
1 | Charts | Automatically map between the Start and End if greater than 1 day. These also show the current progress %.
2 | Milestones | If a Start and End day are set to the same day, this will be reflected as a milestone instead of a chart.
3 | Delivery Dates | Dates where a task is due to finish or with a milestone will be indicated here.
4 | Today | A scrolling marker of today is represented by two red lines
5 | Weekends | Weekends are coloured differently, and can either be hidden or left expanded.
1
2
3
4
5
1
2
3
4
4
5
1
1
2
3
4
5
6