Communities of Excellence—Benefits Realisation Plan

| Prepared | 7 August 2020 |
| --- | --- |
| By | Ann Author |
| For | Alex Sample |
| Document version | Draft 001 |

Purpose of this document

This Benefits Realisation Plan will help to achieve the intended benefits for the project. It captures the benefits that the project aims to produce and outlines how these benefits will be measured and evaluated, so that we know when they have been realised.

The Benefits Realisation Plan also tracks who is responsible (owns) each benefit, the target dates for achieving them, how project initiatives map into intended benefits, and identifies dependencies that need to be considered or addressed.

This is a living document that will be maintained throughout the project, as new initiatives are raised or opportunities for additional benefits are presented.

Benefits Realisation Plan

| ID | Benefit | Beneficiaries | Indicators | Baseline measures | Owner | Target date | Initiatives | Dependencies |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 01 | Shift active health users along the participation continuum | Health consumers, Health professionals, Health services, Government | Number of consumers in the Community of Excellence participating. | Count of consumers (in Community of Excellence locality) moving from Stage 1 to Stage 2 (initial stage), and Stage 5 to Stage 6 (final stage) on the participation continuum, both measured via consumer My Health Record usage | Director of Communities of Excellence |  | My Health Record—Provider side initiatives (awareness, registration & configuration, training & behaviour change for clinicians, training for organisations) Secure Messaging—Provider side initiatives (provider-to-provider, awareness, change management, education, training & behaviour change for clinicians) | Training activities will be conducted by a delivery partner. Healthcare providers need to be using or adopting conformant software to integrate with My Health Record. Healthcare providers and consumers need to be using devices compatible with Secure Messaging software. |
| 02 | Shift professionals along the provider continuum | Health consumers, Health professionals, Health services, Government | Count of professionals in Community of Excellence locality increasing | Count of professionals (in Community of Excellence locality) moving to Stage 3 and Stage 5 | Director of Communities of Excellence |  | My Health Record—Consumer- & provider-side initiatives (awareness, registration & configuration, digital health literacy or training & behaviour change, training for organisations, evaluation) | Digital health literacy education will be conducted by a delivery partner. Provider training activities will be conducted by a delivery partner. Healthcare providers need to be using or adopting conformant software to integrate with My Health Record. |
| 03 | Elimination or mitigation of some health service delivery pain points | Health consumers, Health professionals, Health services, Government | Count of pain points eliminated | Count of pain points identified | Chief Operating Officer |  | My Health Record—Consumer- & provider-side initiatives Telehealth—Consumer awareness; Provider change management e-Prescriptions—Provider awareness | Digital health literacy education will be conducted by a delivery partner. Provider training activities will be conducted by a delivery partner. Healthcare providers need to be using or adopting conformant software to integrate with My Health Record. Healthcare providers and consumers need to be using devices compatible with Telehealth and e-Prescription software. |
| 04 | More sophisticated discourse on the community health (participants, providers, and community leaders) | Health professionals, Health services, Government | Sentiment | Sentiment survey of community leaders and professionals | Director of Communities of Excellence |  | All initiatives | As above Requires enough participants in the survey (large enough sample) to detect significant results. |
| 05 | Enhanced patient self-management | Health consumers | Consumers’ digital health activity | Survey of consumers’ digital health activity (self-reported) My Health Record usage statistics | Director of Communities of Excellence |  | My Health Record—Consumer- & provider-side initiatives e-Prescriptions—Consumer awareness Secure Messaging—Consumer awareness, Consumer & provider communication Telehealth—Consumer awareness | Training activities will be conducted by a delivery partner. Healthcare providers need to be using or adopting conformant software to integrate with My Health Record. Healthcare providers and consumers need to be using devices compatible with Secure Messaging software. |
| 06 | Improved systems through secondary use of data | Health professionals, Health services, Government | Complete, accurate and timely health data | Health statistics | Chief Operating Officer |  | My Health Record—Provider-side training | Training activities will be conducted by a delivery partner. |
| 07 | Avoided duplication of pathology & diagnostic imaging services | Health consumers, Health services | Decrease in associated pathology and diagnostic imaging costs | Current costs for pathology and diagnostic imaging | Director of Communities of Excellence |  | My Health Record—Provider-side initiatives | Training activities will be conducted by a delivery partner. Healthcare providers need to be using or adopting conformant software to integrate with My Health Record. |
| 08 | Increased adherence to evidence-based care | Health consumers, Health professionals | Healthcare provider feedback | Survey of healthcare providers | Director of Communities of Excellence |  | My Health Record—Consumer patient journey maps My Health Record—Provider-side initiatives | Training activities will be conducted by a delivery partner. Healthcare providers need to be using or adopting conformant software to integrate with My Health Record. |
| 09 | Avoided adverse drug events | Health consumers, Government | Decrease in adverse drug events | Current adverse drug events statistics | Director of Communities of Excellence |  | My Health Record—Provider-side initiatives e-Prescriptions—provider registration & configuration | Training activities will be conducted by a delivery partner. Healthcare providers need to be using or adopting conformant software to integrate with My Health Record. Healthcare providers and consumers need to be using devices compatible with e-Prescription software. |
| 10 | Reduced time communicating with health professionals | Health consumers, Health professionals | Healthcare provider feedback | Survey of healthcare providers | Director of Communities of Excellence |  | My Health Record—Provider-side initiatives Secure Messaging—Provider-side initiatives | Training activities will be conducted by a delivery partner. Healthcare providers need to be using or adopting conformant software to integrate with My Health Record. Healthcare providers and consumers need to be using devices compatible with Secure Messaging. |
| 11 | Continuity of communication between patients and health professionals | Health consumers, Health professionals | Healthcare provider feedback Consumer feedback | Survey of healthcare providers Survey of health consumers | Director of Communities of Excellence |  | Secure Messaging—Consumer awareness, evaluation & assessment; Consumer & provider communication | Healthcare providers and consumers need to be using devices compatible with Secure Messaging. |
| 12 | Time and cost savings for patients | Health consumers | Health statistics | Current reported costs and time spent on healthcare | Director of Communities of Excellence |  | My Health Record—Consumer- & provider-side initiatives e-Prescriptions—Provider awareness Telehealth—Consumer & provider awareness | Training activities will be conducted by a delivery partner. Healthcare providers need to be using or adopting conformant software to integrate with My Health Record. Healthcare providers and consumers need to be using devices compatible with e-Prescriptions & Telehealth. |