Communities of Excellence—Project Evaluation Plan

| Prepared | 30 June 2021 |
| --- | --- |
| By | Ann Author |
| For | Sam Sample |
| Document version | Draft 001 |

Disclaimer

Please note that this document is provided as an example only. The organisations identified are only provided to help illustrate how the document can be filled out and may not be relevant to your Community of Excellence (CoE).

Abbreviations and acronyms in this document not otherwise defined in-text

| Abbreviation / Acronym | Stands for… |
| --- | --- |
| ACD | Advanced Care Directive |
| ADHA | Australian Digital Health Agency |
| ALIA | Australian Library and Information Association |
| DHL program | Digital Health Literacy program |
| DICE team | Digital Inclusion and Community Engagement team |
| GTF | Good Things Foundation |
| HCP | Healthcare professional |
| MBS | Medicare Benefits Schedule |
| MHR | My Health Record |
| PHN | Primary Health Network |
| R&E team | Research and Evaluation team |
| SM | Secure Messaging |

Project Evaluation Plan

| Evaluation question | Measure | Regularity | Data source | Responsibility |
| --- | --- | --- | --- | --- |
| - Process |  |  |  |  |
| - Were all the activities delivered? - Was tailored educational/training content developed and delivered? | Number of networking/education/training events/sessions delivered (by type e.g. webinar, face-to-face) | Quarterly | Progress reports Service records, such as records of when sessions/events were held, number of participants etc. | PHN to retrieve data and share with ADHA R&E team ADHA (through the DICE team) to retrieve data and share with the CoE team & R&E team |
| - Reach – Healthcare professionals |  |  |  |  |
| - Were HCPs reached as intended? - Were HCPs satisfied with the education/training? - HCP aware/engaged with CoE? - Were HCP aware of local support for digital technologies? - To what extent did knowledge of digital technology and benefits increase among HCPs? - Were HCPs willing to adopt digital technology? | - # HCP attending training by setting - Number of HCPs attending education and networking events by stakeholder group - Satisfaction with services/education/training - # of HCPs registered for further communications/education session - Number of HCPs requesting digital health information or technical support - % HCPs reporting changes in awareness, knowledge, attitudes and satisfaction with MHR, telehealth, SM - % HCPs willing to adopt new technology - % HCPs that can correctly recall benefits of each technology | Quarterly | Service records, such as records of when sessions/events were held, number of participants etc. HCP pre/post survey HCP interviews and case studies | PHN/ADHA to retrieve data and share with ADHA R&E team |
| - Reach – Consumers |  |  |  |  |
| - Were consumers (patients or families) satisfied with the education/training? - Consumers aware/engaged with CoE? - Improved consumer awareness and trust of MHR - Consumers confident in ability and capacity to use MHR - Consumers attend digital health literacy workshops - Consumers aware of MHR support and information available locally and online - To what extent has knowledge and awareness changed? | - Satisfaction with services/education/training - Utilisation of support services - # of consumers registered for further communications/education session - % consumers reporting changes in awareness, knowledge, attitudes and trust of MHR - # consumers attending digital health literacy training - # consumers that contact PHN for MHR information and technical support. - # consumers visit the ADHA/MHR website, use online tools - # factsheets distributed/uploaded - Website activity | - Quarterly | Service records Consumer post survey (DHL Program) Consumer interviews and case studies | ADHA R&E team to design survey PHN/ADHA/DICE/ALIA/GTF to retrieve data and share with ADHA R&E team |
| - Outcomes – HCPs |  |  |  |  |
| - How has MHR use changed over time? How does this compare to the state average? How does this compare to control-site? [continued next page] - How many healthcare provider organisations (across all sectors) are connected and utilising the various documents within My Health Record | - % of healthcare HCPs registered by setting - # HCP organisation uploads per month, by type of document and setting - Number of documents viewed per month, by setting - % healthcare HCPs viewing, by setting - Number of times documents uploaded by healthcare HCP has been viewed by a different service HCP - Number of unique records accessed - Number of documents uploaded per month by HCP - Average number of Shared Health Summary, Discharge Summary, Event Summary, Pathology & DI reports, Prescription records uploaded by setting (hospital, specialist practices, general practices, pharmacies) - # consecutive weeks with 1+ views/upload by organisation - My Health Record Utilisation Intensity Index - # individuals who have had their record accessed by 2+ HCPs | Quarterly | - HCP registration and utilisation data (Service Design Team) | ADHA CoE project team to retrieve data and share with R&E team |
| - Were there changes to policy practices? - Has the program changed routine processes? | - HCPs develop organisational policies to deliver MHR/telehealth | Quarterly | Service records HCP interviews and case studies | ADHA R&E team to design survey, design and conduct (if possible) interviews PHN/ADHA/DICE/ALIA/GTF to retrieve data and share with ADHA R&E team |
| - Were there documented improvements in efficiency? - Were benefits in connecting Did HCP organisations report benefits of adopting digital health technology? | - Self-report reduction in time spent gathering information/contact details - Reduced time communicating with other HCPs - Reduced referral for pathology and/or diagnostic imaging etc.)? - Improved coordination of care? | Quarterly | HCP pre/post survey HCP interviews and case studies MBS data? | ADHA R&E team to design survey, design and conduct (if possible) interviews PHN/ADHA/DICE/ALIA/GTF to retrieve data and share with ADHA R&E team |
| How has SM use changed over time? | HCPs using SM to send referrals by setting | Quarterly | HCP pre/post survey HCP interviews and case studies MBS data? | ADHA R&E team to design survey, design and conduct (if possible) interviews PHN/ADHA/DICE/ALIA/GTF to retrieve data and share with ADHA R&E team |
| - Outcomes – Consumers |  |  |  |  |
| - To what extent have consumer MHR behaviours changed? - Is more comprehensive patient information accessible in MHR? - Do consumers have access to services from home and remote settings? - Improved patient experience - Did consumer health literacy improve? - Did consumers have increased confidence to manage their own health? | - % individuals viewing their MHR - % with consumer entered health information - # documents viewed by consumers (e.g. ACD, audit view, immunisation register, organ register) - # consumer document uploads - # of virtual care and/ or telehealth services - Self-reported reduction in travel - Self-reported improvement in patient experience - Self-report - Knowledge testing - Self-reported increased confidence to manage their own health. | - Quarterly | Consumer use data Consumer post survey Consumer interviews and case studies | ADHA R&E team to design survey, design and conduct (if possible) interviews PHN/ADHA/DICE/ALIA/GTF to retrieve data and share with ADHA R&E team |