# Emerald Communities of Excellence—Allied Health Engagement Plan

| Prepared | 30 June 2021 |
| --- | --- |
| By | Ann Author |
| For | Sam Sample |
| Document version | Draft 001 |

This example focuses specifically on engaging Allied Health (AH) Professionals / organisations.

Disclaimer

Please note that this document is provided as an example only. The organisations identified are only provided to help illustrate how the document can be filled out and may not be relevant to your CoE.

Abbreviations and acronyms in this document not otherwise defined in-text

| Abbreviation / Acronym | Stands for… |
| --- | --- |
| ADHA | Australian Digital Health Agency |
| AH | Allied Health |
| AHPA | Allied Health Professions Australia |
| CHRC | Central Highlands Regional Council |
| CoE | Community of Excellence |
| COVID | COVID-19 / SARS-CoV-2 (sudden acute respiratory syndrome coronavirus 2) |
| CQRH | Central Queensland Rural Health |
| EMG | Emerald Medical Group |
| FB | Facebook |
| GP | General Practitioner |
| MHR | My Health Record |
| NDIS | National Disability Insurance Scheme |
| PHN | Primary Health Network |

Contents

Introduction	3

Purpose	3

Engagement Objectives	3

Target Audiences	4

Strategy	4

Key Messages	5

CoE Messaging:	5

Benefits to Allied Health:	5

Scope 	6

1	Audience	8

1.1	Stakeholder Mapping	8

1.2	Media and Communication Channel Identification	11

2	Engagement and Event Strategy	12

2.1	Local Health Provider Activities and Events	12

2.2	Collateral Pool	14

3	Identification of good news stories and local champions	15

Timeline for PHN Provider Engagement (Allied Health) and Communications	16

Contracted Deliverables related to Allied Health Engagement	17

Introduction

The Australian Digital Health Agency, in collaboration with Central Queensland, Wide Bay, Sunshine Coast PHN (CQWBSC PHN) and other delivery partners and stakeholders, will work with the Emerald community to:

- Connect all healthcare providers in Emerald to the national My Health Record system and train them on how to use it and how it will benefit the community

- Run a digital literacy program for Emerald residents to empower them to take advantage of the benefits of digital health

- Showcase Emerald as a model for building digital health Communities of Excellence that can be replicated across Australia

This important initiative and will require direct engagement at a local level to ensure all healthcare providers are informed about the Communities of Excellence program and the benefits of digital health tools to improve health outcomes.

CQWBSC PHN has been identified as a key delivery partner to coordinate and facilitate local engagement within the Emerald community.

Purpose

This plan will outline the delivery and implementation of the local healthcare provider engagement and communications activities for CQWBSC PHN as a part of the Emerald Communities of Excellence Program. This plan will have a specific focus on Allied Health engagement.

Engagement Objectives

To support the overarching objectives of the Emerald Communities of Excellence program, the CQWBSC PHN Allied Health Engagement strategy encompasses the following objectives:

- To inform and educate the Emerald healthcare community of the Communities of Excellence Program.

- To raise awareness of the benefits of My Health Record, Telehealth and Secure Direct Messaging for healthcare providers in Emerald.

- To encourage and support an increase uptake and meaningful use of the aforementioned digital health tools with Emerald healthcare providers.

- To ensure healthcare providers are aware of communications collateral available to support consumers to use digital health tools.

- Enhance the digital connectivity between health practitioners and between health practitioner and the community/their patients to facilitate better health outcomes.

- Increase demand for the uptake of digital health tools via the consumer, GPs and community champions.

Target Audiences

The target audience will be healthcare professionals that provide services to the Emerald community. Engagement will be prioritised based on the organisation structure as described below:

- Providers that have businesses registered in Emerald

- Providers that have businesses in Emerald but registered within the PHNs catchment area

- Providers with complex organisation structures (i.e. head office is located in a metropolitan area) – engagement activities should cover education and awareness activities rather than registration and use.

Strategy

The proposed strategy comprises a mix of activity within the Emerald community and identifies communication channels to engage with specific healthcare providers. This includes identifying channels and undertaking targeted activities at the local level.

The engagement strategy also expands into exploring the identification of good news stories and local champions, a calendar of local events and a refined collection of key messages and collateral to support engagement.

Broadly, communication activities can be broken into three phases:

- Stage One – Planning & Continuation of Awareness (September & October 2020)

Landscape analysis and re-engagement with local provider organisations and healthcare providers – awareness of the project and its purpose. Promotion of digital health tools and phase 1 progress. Include general face to face greater healthcare provider event – “Greater healthcare connectivity through digital health tools” (secure messaging, MHR, telehealth).

- Stage Two – Promotion & Education (Oct 2020 to April 2021)

Engage organisations and providers for the education and promotion of digital health tools. Face to face engagement to be prioritised. Utilise community champions, GPs and organisations (e.g. ADHA, AHPA, professional bodies) to help facilitate and influence digital health tool adoption and organisational change.

Provide direct (preferably face to face) education at an organisation and provider level regarding how to use and the importance of digital health tools. Further promotion of the benefits of digital health. Drive an increased demand for digital health through the promotion of AH digital health capabilities at GP and consumer levels.

- Stage 3 – Meaningful use & transition into business as usual

Follow up directly with providers to review use, further education. Work will be completed in this stage to ensure that digital health systems are used in a meaningful way by allied healthcare providers in Emerald (i.e. actively viewing MHR, confident in using telehealth, regularly using secure messaging) Evidence of this will be collected through the govdex data as well as good news stories as expressed by the providers.

Key Messages

CoE Messaging:

- Uptake of digital health tools to benefit the greater community and improve quality of care

- Improve connectivity between healthcare providers and between healthcare providers and the community through the meaningful use of digital health tools

- Facilitate an increase in demand for digital health tool use by AH providers. MHR – consumer and GP driven, secure messaging – GP driven, telehealth – consumer and GP driven

- A digitally connected and collaborative healthcare community

- A digitally responsible healthcare community

- A digitally aware and knowledgeable AH workforce capable of informing and educating the public in the use of digital health tools

Benefits to Allied Health:

- Improved quality of care for patients

- Business development – increased market and service reach (improved accessibility for patients to service via telehealth)

- Future preparedness in a constantly developing healthcare landscape

- Access to greater customer base in particular through the use of Telehealth

- Improved connectivity between healthcare providers

- Time saving (direct access to patient history, imaging, medications etc via MHR)

- Improved referral stream, increased efficiency and improved patient data security through secure messaging

Scope

| In Scope (deliverables) | Out of Scope |
| --- | --- |
| Direct healthcare provider engagement (face to face, phone, email) Promotion within community Identify profession specific digital health champions Organising events Identify what is important to health providers. Tailor specifically for this, otherwise create importance. Describe focus – customers, markets, products, locations, or processes: Digital health tools. My Health Record, secure messaging, telehealth Allied health Facilitator professions/groups: NDIS support services, GPs, consumer, hospital What we need to produce: Events Promotional material Key contacts Time Resources for events | High-level discussions with national and state level organisations not based in Emerald Direct face to face engagement with organisations who visit Emerald only/outside of geographical region Additional tasks outside of deliverables exhaustive of capacity |

| Assumptions | Constraints |
| --- | --- |
| That all healthcare organisations are willing to participate and be engaged All community organisations are covered/mapped in the plan | Limited healthcare organisation time and low prioritisation allocated to adoption of new digital health tools Potential resurfacing of COVID restrictions could impact face to face engagement Pre-conceived ideas regarding digital health security (MHR and telehealth) Inability to access meaningful information via My Health Record e.g. diagnostics, imaging Incompatible clinical software (My Health Record) Dependencies Lessons Learned Review |

| Dependencies | Lessons Learned Review |
| --- | --- |
| Sufficient community and healthcare provider/organisation buy-in A willingness of healthcare providers to adopt new work practices Project staff on the ground in Emerald Consistent messaging from all stakeholders Ability to engage via multiple channels, including face to face Sufficient funding to complete activities Increased demand for digital health tool use | Face to face meetings are more powerful than phone or email communications Project buy-in is dependant influenced by healthcare provider/organisation connection to community Medium and large organisations are more difficulty to influence/instil change i.e. MHR registration Smaller local businesses have limited time to allocate to additional administrative tasks Speaking directly to healthcare providers additionally to organisation and administration/managers is important to drive demand There is a need to increase awareness of digital health tools (GP and community) to increase demand |

# Audience

## Stakeholder Mapping

Identify stakeholder organisations and groups in Emerald that you will leverage to deliver provider support, focusing on priority areas and target audiences outlined above.

| Organisation name | Organisation affiliation (local, state, or national body) | Profession type | Organisation activities | Target audience / Special area of interest | Contact details |
| --- | --- | --- | --- | --- | --- |
| e.g., [Name redacted] | NDIS | Psychology | Early childhood – early intervention (ECEI) Drop-in services Assessment for children under 7 years | Early childhood |  |
| [Name redacted] |  | Physiotherapy | Community / private practice physiotherapy services Occupational physiotherapy services | Emerald community Industry (e.g., mining) | Name [redacted] Name [redacted] (Receptionist) E: _____________ P: _____________ |
| [Name redacted] |  | Occupational therapy | Community / private practice | Emerald community | Name [redacted] E: _____________ P: _____________ |
| [Name redacted] |  | Speech Pathology | Community / private practice | Emerald community | Name [redacted] E1: ____________ E2: ____________ P: _____________ |
| [Name redacted] (EMG psychologist) | Emerald Medical Group | Psychology | Provisional psychologist (community) Child psychology specialist training | Emerald community | P: _____________ |
| [Name redacted] | Emerald Medical Group | Psychology | Community | Emerald community | Name [redacted] E: _____________ P: _____________ |
| [Name redacted] |  | Podiatry | Community | Emerald community | Name [redacted] Name [redacted] (admin officer) E: _____________ P: _____________ |
| [Name redacted] | Priority Health Group | Dietetics | Community | Emerald community | Name [redacted] E1: ____________ E2: ____________ P: _____________ |
| [Name redacted] | Therapy PRO | Psychology | Community | Emerald community | Name(s) E: _____________ P: _____________ |
| [Name redacted] |  | Physiotherapy | Community Occupational therapy | Emerald community | P: _____________ |
| [Name redacted] |  | Dietetics | Community | Rockhampton / NQ | Name [redacted] Name [redacted] E1: ____________ E2: ____________ P: _____________ |
| [Name redacted] | NDIS | Allied health general | Community | Regional NSW and QLD | Name [redacted] Name [redacted] (dietician, driving MHR interest in Emerald office) E1: ____________ E2: ____________ P: _____________ |
| [Name redacted] |  | Allied health general | Community | Central & Northern QLD | Name [redacted] E: _____________ P: _____________ |
| [Name redacted] | NDIS | NDIS support service | Community | Emerald | E: _____________ P: _____________ |
| [Name redacted] |  | Oral health / dentistry | Community | Emerald | P: _____________ |
| [Name redacted] |  | Oral health / dentistry | Community | Emerald | P: _____________ |
| [Name redacted] |  | Oral health / dentistry | Community | Brisbane / Emerald | P: _____________ |
| [Name redacted] |  | Oral health / dentistry | Community | Emerald | P: _____________ |

## Media and Communication Channel Identification

| Name of media outlet | Media type | Contacts | Frequency |
| --- | --- | --- | --- |
| Social media – Facebook | Consider – CHRC, community FB pages/groups, PHN, CQRH, EMG, other health business pages, advertising. Encourage local businesses to advertise availability of MHR access. Paid vs. unpaid | - Community FB pages: Emerald Community Awareness Emerald Buy Swap Sell Emerald – Raves Praise & Hooray’s! CQRH – [name redacted] CHRC | Weekly/monthly |
| Highlands Leader | Newspaper / print media | [Name redacted] (CQRH) [Name redacted] (Highlands Leader) | 1-2 x duration of project |
| 4HI | Local radio | - 1300 305 918 | 1-2 x duration of project |
| N/A | Podcast | - N/A | Bimonthly x duration of project |
| Emailing lists PHN emailing lists CHRC emailing list / e-news bulletin (community engagement) Local community contact lists | Email | - N/A | Monthly |
| Health organisations Emerald Hospital | Posters / printed material | - [Name redacted] | 3-monthly |
| AH organisations | Phone | - See stakeholder mapping | Monthly |
| AH organisations | Face-to-face | - See stakeholder mapping | Monthly |

# Engagement and Event Strategy

## Local Health Provider Activities and Events

| Event | Date | Location | Logistics / Resources |
| --- | --- | --- | --- |
| Contact & reintroduce CoE project + team to AH and specialists in community | 1/10/2020–20/10/2020 | N/A | [Name redacted] – email & phone contact to each organisation |
| Face to face visit / drop-in with flyers for promotion of event | 1/10/2020–20/10/2020 | N/A | [Name redacted] Flyers printed |
| CoE phase 2 “kick-off” event. Focus on collaboration between health professionals and how digital health tech facilitates this: GP–AH, AH/pharmacy GP/pharmacy. Secure messaging, MHR. Improving collaboration and optimising expertise within our community via digital health. Gauge interest in further engagement opportunities with quick survey. +/- include consumer invite (numbers restrictions may prohibit) | 21/10/2020 | Maraboon Motor Inn Mayfair Tavern Town Hall | ADHA AHPA [medical software] representative GP practice manager ([name redacted]) PHG representative Dr [Name redacted] Other GP [Name redacted] – pharmacy [Name redacted] – physio/ AH [name redacted] / [name redacted] Funding Advertising Steering Committee |
| AH drop-in casual breakfast/coffee to discuss digital health further following kick-off | 22/10/2020 | Sensory Gateway Hotel | Funding |
| Phone call / practice visit to follow up regarding interest in lunch & learn session | 23/10/2020–30/10/2020 | N/A | [Name redacted] |
| Lunch & learn sessions – clinic specific. Invite from kick-off event +/- specialist visits | 30/10/2020–project end | N/A | [Name redacted] |
| Practice visits / catchups | 30/10/2020–project end Ad hoc – 1x bimonthly | N/A | [Name redacted] |
| Promotion of Allied Health digital health capabilities to GP | 23/10/2020–project close / ad hoc | Consider events e.g., CQRH weekend | Emailing lists [Name redacted] [Name redacted] |
| Promotion of Allied Health digital health capabilities to consumers | Ad hoc | Consider community events e.g., Christmas markets | [Name redacted] Steering Committee Social media channels Posters in key locations |
| NDIS support providers (e.g., [name redacted], [name redacted], [name redacted]) digital health education – how it can support clients. (Lunch & learn) | 23/10/2020–project end (aim for by end of calendar year) | At organisation facilities / offices | [Name redacted] [Name redacted] |
| Interview with local champions / user (possible AH, GP, consumer) good news stories—to be shared on different platforms e.g., podcast / webinar / video | 2021 | N/A | [Name redacted] [Name redacted] |

## Collateral Pool

List of collateral that will be used to support engagement.

Consumer support – increase demand of digital health services/capabilities ([Name redacted])

GP practice support – as above ([Name redacted])

Steering Committee

AHPA – encourage uptake

Clinical software

[Medical software provider] – [Name redacted] (sales representative)

PHN x ADHA allied health webinar “Using technology to enhance business and improve levels of care”

Funding (ADHA) – lunch & learn, events (venue hire & catering), breakfast drop-in

Advertising – printing, media

Telehealth Hub – https://digitalhealthcrc.com/telehealth/

AHPA - https://ahpa.com.au – digital health inclusion tool, telehealth guide, connection guides (MHR), Digital health webinars (dietetics, physio & psychology), digital health policy templates (dietetics, physio & psychology), digital health toolkits

My Health Record - https://www.myhealthrecord.gov.au – including step guides for registration

ADHA - https://www.digitalhealth.gov.au/using-the-my-health-record-system - including training resources; My Health Record Help line: 1800 723 471; https://conversation.digitalhealth.gov.au/communities-of-excellence-emerald - CoE project.

[Name redacted] (Telehealth physio) – [webpage] (list of research articles relating to telehealth)

[Name redacted] YouTube channel – [URL redacted]

[Name redacted] webinar – [URL redacted]

Australian Physiotherapy Association - https://australian.physio/telehealth (including telehealth funding streams)

Telehealth and Medicare claiming (webinar) – Allied Health

# Identification of good news stories and local champions

Ensure you address the following requirements with regard to identification of good news stories and local champions:

- Identify and communicate local success stories (good news stories) to the Agency team for potential development into video case studies

- Identify and communicate local champions to the Agency team with a view to them becoming an advocate for My Health Record and attend events and/or town halls. These champions could be:

- Healthcare provider using the My Health Record system/digital health technologies

- An individual with a trusted voice in the community

- An individual who has a profile with a specific audience

Consider possible good news stories:

Secure messaging between allied health and pharmacy

Secure messaging between allied health and general practice – facilitating healthcare connectivity as well as patient data security

People with NDIS plans being able to access healthcare through telehealth when unable to be in community. Health providers able to access information through MHR

Allied health, specialists and GP’s able to freely communicate and collaborate in the delivery of patient care e.g. virtual care

Telehealth - connecting rural and remote Queenslanders to health care

Access to My Health Record enables allied health provider to better understand patient (NDIS)

Timeline for PHN Provider Engagement (Allied Health) and Communications

| Stage | Date | Activities |
| --- | --- | --- |
| Stage One – Planning & Continuation of Awareness (September & October 2020) | 1/10/2020–23/10/2020 | Re-introduction of project phone & email Establish contact directly with providers as well as organisations where possible Promotion of kick-off event—practice visit / flyer drop-off CoE phase 2 kick-off event Gauge interest at event for lunch & learn sessions Breakfast/coffee drop-in for AH |
| Stage Two – Promotion & Education (October 2020 to April 2021) | 23/10/2020–31/12/2020 | Contact organisations to review current status, organise lunch & learn sessions Lunch & learn sessions |
|  | 1/01/2021–project close | Facilitate registration with MHR, utilisation of secure messaging, implementation of telehealth capabilities—promotion, collaboration with key influencers / local legends e.g., [Name redacted] Increase consumer awareness of digital health capabilities—collaboration with [Name redacted] |
| Stage Three – Meaningful use & transition to BAU | 2021 | Direct follow-up with providers and organisations to review use Increase meaningful use. Further education on use of MHR. Practice/organisation visits Direct engagement with providers Good news story shares Interview / podcast / video |

Contracted Deliverables related to Allied Health Engagement

D1. Continued employment of local project officer and an Allied Health professional

D2. Landscape analysis of all healthcare providers and capturing software, contact details, MHR status, electronic prescribing status, secure messaging and any telehealth use

D3.1 Review and distribute surveys from the Agency and other delivery partners

D5. Consult with the steering group to identify virtual care deliverables, create a plan and execute

D6. Work with delivery partners such as ACCRM and AHPA to deliver events, education materials etc to the community

D7. Work with the Agency and partners to coordinate the stepped care model in relation to mental health between GPs, Specialist and Allied Health including Psychologists.

D8. Further encourage secure messaging and telehealth uptake in Emerald between healthcare providers

D9. Promote relevant Agency materials and resources to the PHN database such as the mental health compendium, Communities of Excellence toolkit etc when they are released

D9.1 Identify relevant good news stories/quotes/case studies for the Agency to pursue

D10. Collaborate on priority group mapping of local health and community activities.

D11. Provide introductions / establish local relationship and support ongoing engagement for stakeholders identified in priority group mapping.

D13. Explore and help localise digital health ideas / solutions / proposals for action with the Agency as a result of the co-design activities.

D17. Coordinate an annual public session and associated messaging that updates residents on the program, the progress so far and opportunities and benefits for the local community until the program's close.